## Jira WSR
WEEKLY ENGINEERING STATUS REPORT
Sprint 101 status extract ¦ Source: sprint_101_status_updated.csv
Report period | Sprint 101 |  | Status rationale | Amber reflects 98 non-Done issues and 15 active production bugs.
Team | HA30 Engineering
Overall status | Amber
As of | 2026-09-08
1. Completed This Week | 1. Completed This Week | 1. Completed This Week | 1. Completed This Week
Metric | Value |  | Issue type | Count
Total issues in extract | 222 |  | Bug | 84
Done | 124 |  | Task | 92
Completion rate | 55.86% |  | Story | 41
Production bugs total | 21 |  | Improvement | 5
Production bugs still active | 15 |  | Deployment-tagged | 12
Active issues | 98 |  | QA automation | 10
2. In Progress | 2. In Progress | 2. In Progress | 2. In Progress
Status | Issue count | Production bugs | Share of extract
New / Open | 38 | 5 | 17.12%
In Progress | 29 | 1 | 13.06%
Ready for Testing | 16 | 7 | 7.207%
HerdX Accepted | 11 | 1 | 4.955%
Rejected / Not a Bug | 2 | 0 | 0.9009%
Cannot Reproduce | 1 | 1 | 0.4505%
Discarded | 1 | 0 | 0.4505%
Total not Done | 98 | 15 | 44.14%
3. Blocked or At Risk | 3. Blocked or At Risk | 3. Blocked or At Risk | 3. Blocked or At Risk
Risk / issue | Count | Action / reference
Active production bugs | 15 | See Active Issues tab; production risks are sorted first.
New / Open issues | 38 | Triage and plan.
In Progress issues | 29 | Continue development and confirm next milestones.
Ready for Testing | 16 | Complete QA validation.
Unassigned active issues | 5 | Assign owners; see Attention column.
4. Release / Deployment Updates | 4. Release / Deployment Updates | 4. Release / Deployment Updates | 4. Release / Deployment Updates
Metric | Count | Notes
Deployment-tagged issues | 12 | Includes release and deployment work.
Deployment-tagged Done | 10 | Completed deployment items in the extract.
Deployment-tagged still open | 2 | Follow up on remaining deployment work.
QA automation still open | 2 | Regression items not yet Done.
5. Next Week's Focus | 5. Next Week's Focus | 5. Next Week's Focus | 5. Next Week's Focus
Focus area | Recommended action | Basis
Production defects | Prioritize active production bugs and confirm ownership. | 15 active production bugs
Testing pipeline | Close or retest items currently Ready for Testing. | 16 Ready for Testing
Open backlog | Triage New / Open items and assign the unowned work. | 38 New / Open; 5 unassigned active issues
Source note: The CSV contains issue status, ownership, labels, and production-bug flags, but no issue dates, estimates, due dates, or sprint timestamps. Counts therefore reflect the supplied Sprint 101 extract rather than a dated weekly delta.

## Active Issues
ACTIVE ISSUES
All records with Status other than Done, sorted with production bugs first. Use this tab for the detailed In Progress and at-risk view.
Key | Summary | Issue Type | Assignee | Status | Labels | Production Bug | Attention | Next Step
HA30-13493 | Norton Client Issue in Production - Assigned Tag Range Displayed as "Not Assigned" in Add to Inventory Flow | Bug | Praveen Francis | New / Open | App, Dev, Prod, QA | Yes | Production risk | Triage and prioritize production fix
HA30-14422 | Prod -Web ,For Location Operation User other location records were displayed | Bug | gangappan | New / Open | App, Prod, QA, dev, web | Yes | Production risk | Triage and prioritize production fix
HA30-14798 | Prod Issue - Customer Issue - Animals Missing in the Chute session | Bug | Praveen Francis | New / Open | App, Dev, Prod, QA | Yes | Production risk | Triage and prioritize production fix
HA30-15131 | PROD: Calving Filter Is Not Working | Task | gangappan | New / Open | App, Dev, QA | Yes | Production risk | Triage and prioritize production fix
HA30-15198 | Cedaco Range Issue - HSR is not assigned to their organization | Bug | Abraham | New / Open | App, Dev, Prod, QA | Yes | Production risk | Triage and prioritize production fix
HA30-15008 | Azure Cost Analysis – Databricks Long-Running Job | Bug | Gladys Kirubavathi | In Progress | Analytics, Prod | Yes | Production risk | Continue production fix
HA30-14471 | Prod - MedicineInventory - Other medicine type not listed in user medicine, Old version if we update other medicine type , its shown blank in new app | Bug | Samuel Parker | Ready for Testing | App, Dev, Prod, QA | Yes | Production risk | Complete production validation
HA30-14779 | Prod : Treatment history continuous sync | Bug | Samuel Parker | Ready for Testing | App, Dev, Prod, QA | Yes | Production risk | Complete production validation
HA30-15029 | Bugs with Adding Sources | Bug | Samuel Parker | Ready for Testing | App, Dev, Prod, QA | Yes | Production risk | Complete production validation
HA30-15171 | Feed Information Now Showing Up in Ogle Farms | Bug | Samuel Parker | Ready for Testing | App, Dev, Prod, QA | Yes | Production risk | Complete production validation
HA30-15172 | Tag IDs not Showing Up in Inventory During Chute Session | Bug | Samuel Parker | Ready for Testing | App, Dev, Prod, QA | Yes | Production risk | Complete production validation
HA30-15226 | Prod Web: Deleted Tag – Deleted Date Ascending/Descending Sort Filter Not Working | Bug | Alpa Mori | Ready for Testing | App, Dev, Prod, QA | Yes | Production risk | Complete production validation
HA30-15257 | Production: Activity log- Upload Excel ,Under Treatment details should not be shown | Bug | Allwin. T | Ready for Testing | Dev, Prod, QA | Yes | Production risk | Complete production validation
HA30-15100 | PROD: Cedaco Ranch - Counting Session Export Issue | Bug | Candace Adams | HerdX Accepted | App, Dev, Prod, QA | Yes | Production risk | Confirm disposition and close
HA30-15070 | Prod - Not able to create location to location Transfer | Bug | Abraham | Cannot Reproduce | App, Dev, Prod, QA, Regression | Yes | Production risk | Confirm reproduction outcome
HA30-13467 | Crash analytics - R6ReaderCardAndroidState.r6Item. | Bug | Abraham | New / Open | App, Dev, Firebase, QA | No | New / Open | Triage and plan
HA30-14249 | ATI - Manual entry - Message needs to be updated when switching from one tag type to another | Improvement |  | New / Open | App | No | Owner needed | Assign owner
HA30-14319 | Export Excel – Improve Alignment of the Glass Tag/Implant Column Within the Additional IDs Group | Improvement | samuel kishore kumar | New / Open |  | No | New / Open | Triage and plan
HA30-14460 | Shift Spacing on Inventory Page for Desktop Version | Improvement | Saravana Kumar M | New / Open |  | No | New / Open | Triage and plan
HA30-14594 | Azure Databricks workspace entitlement changes | Task | Gladys Kirubavathi | New / Open |  | No | New / Open | Triage and plan
HA30-14595 | Access to the Google Cloud console | Task | samuel kishore kumar | New / Open |  | No | New / Open | Triage and plan
HA30-14596 | Investigate inconsistent HSR RFID tag reading performance during load-out at Riley Livestock | Task | Abraham | New / Open |  | No | New / Open | Triage and plan
HA30-14734 | Firebase Extensions decommission on Mar 31, 2027 | Task | samuel kishore kumar | New / Open |  | No | New / Open | Triage and plan
HA30-14833 | Dashboard STR - Implement the functionality for top 4 KPI cards | Story | Alpa Mori | New / Open | App | No | New / Open | Triage and plan
HA30-14898 | Present Animal History Instead of Enclosure Movement History | Story |  | New / Open | App | No | Owner needed | Assign owner
HA30-14977 | Activity Log – Undo Button Is Missing for “Add to Inventory” Activity(TAB VIEW) | Bug | Raji S | New / Open | App, Dev, QA | No | New / Open | Triage and plan
HA30-14979 | Activity Log – “Treatment Added” Records Are Not Displayed and Undo Button is missing (Tab View) | Bug |  | New / Open | App, Dev, QA | No | Owner needed | Assign owner
HA30-14997 | Validate R6 Reader Output Power Based on Detection Setting | Story | Allwin. T | New / Open |  | No | New / Open | Triage and plan
HA30-15040 | Activity Log - Common function for Upload Excel | Story | Alpa Mori | New / Open |  | No | New / Open | Triage and plan
HA30-15073 | Deployment for Sprint 101 | Story | Abraham | New / Open | App, Deployment | No | New / Open | Triage and plan
HA30-15101 | Firebase Crash - View.of FlutterError - Null check operator used on a null value | Bug | Alpa Mori | New / Open | App, Dev, Firebase, QA | No | New / Open | Triage and plan
HA30-15114 | Implement HerdView SnapView Report in Flutter | Story | Muhundhan E | New / Open | App | No | New / Open | Triage and plan
HA30-15142 | SnapView Report - Database Schema architecture & Data migration engine | Story | samuel kishore kumar | New / Open | App | No | New / Open | Triage and plan
HA30-15143 | SnapView Report - Core KPI engine and Financial outcome resolvers | Story | samuel kishore kumar | New / Open | App | No | New / Open | Triage and plan
HA30-15144 | SnapView Report - Distribution Analytics: Time on Yard & Demographics | Story | samuel kishore kumar | New / Open | App | No | New / Open | Triage and plan
HA30-15145 | Real-Time Sync Pipeline, Dead-Letter Queue & Health Engine | Story | samuel kishore kumar | New / Open | App | No | New / Open | Triage and plan
HA30-15146 | Geospatial Mapping Engine & Treatment Medicine Analytics | Story | samuel kishore kumar | New / Open | App | No | New / Open | Triage and plan
HA30-15147 | Filter Discovery, Index Tuning, Caching | Story | samuel kishore kumar | New / Open | App | No | New / Open | Triage and plan
HA30-15149 | Backdate AI Breeding Date | Task | gangappan | New / Open | App, Dev, QA | No | New / Open | Triage and plan
HA30-15156 | Display Informative Message When Deleting a Breed Assigned to Animals | Improvement | samuel kishore kumar | New / Open | App, Dev, QA | No | New / Open | Triage and plan
HA30-15178 | Enable Firebase Crashlytics Reporting in Staging Environment | Story | samuel kishore kumar | New / Open | App | No | New / Open | Triage and plan
HA30-15194 | Chute Session - Save button not enabled for the new tags | Bug | Abraham | New / Open | App, Dev, QA | No | New / Open | Triage and plan
HA30-15196 | Complete Android developer verification registration | Task | samuel kishore kumar | New / Open | App, Dev | No | New / Open | Triage and plan
HA30-15204 | Identify and Disable Unnecessary Report Refreshes and Related Jobs | Task |  | New / Open |  | No | Owner needed | Assign owner
HA30-15211 | Herdview SnapView: Data displayed in HerdView SnapView is not matching between the Web and App versions. | Bug | samuel kishore kumar | New / Open | App, Dev, QA | No | New / Open | Triage and plan
HA30-15212 | HerdView SnapView: Animal Status by Sex/Type : "Vaquilla" Is Incorrectly Displayed | Bug | samuel kishore kumar | New / Open | App, Dev, QA | No | New / Open | Triage and plan
HA30-15220 | Staging Release 5.0.152 (10) for IOS, Android and Web | Task | Abraham | New / Open | App, Deployment | No | New / Open | Triage and plan
HA30-15223 | Duplicate Activities Are Displayed in Activity Log for a Single Chute Session Movement | Bug | gangappan | New / Open | App, Dev, QA | No | New / Open | Triage and plan
HA30-14634 | Counting Session - Performance analysis for storing session data in Reader sessions | Story | Praveen Francis | In Progress | App | No | In Progress | Continue development
HA30-14635 | Counting session - Add Counting session ID in Reader sessions | Story | Praveen Francis | In Progress | App | No | In Progress | Continue development
HA30-14813 | New Automation Development – Assign Medicine to Animals for Pastures from Medicine Inventory | Story | Mariappan E | In Progress | QAAutomation | No | In Progress | Continue development
HA30-14814 | Prevent Data Loss by Stopping Process on Critical Errors in inventory | Story | Praveen Francis | In Progress | App | No | In Progress | Continue development
HA30-14816 | Review and Resolve All Crashlytics Issues in the Chute session | Story | Praveen Francis | In Progress | App | No | In Progress | Continue development
HA30-14822 | Report Story - Treatment report functionality - Mobile & Tab version | Story | Praveen Francis | In Progress | App, POC | No | In Progress | Continue development
HA30-14826 | Investigate Azure ADF Cost Increase and Identify Cost Optimization Opportunities | Task | Gladys Kirubavathi | In Progress | Analytics, App | No | In Progress | Continue development
HA30-14832 | Dashboard STR - UI for Top 4 KPI cards on Dashboard | Story | Praveen Francis | In Progress | App | No | In Progress | Continue development
HA30-14834 | Dashboard STR - Breeds pie chart | Story | Praveen Francis | In Progress | App | No | In Progress | Continue development
HA30-14857 | Activity Log - Display activity type breakdown in pie chart | Story | Praveen Francis | In Progress | App | No | In Progress | Continue development
HA30-14861 | Activity Log - Activities Tabular view UI for Tab and Web | Story | Praveen Francis | In Progress | App | No | In Progress | Continue development
HA30-14870 | Activity log - Implement total activities KPI functionality | Story | Praveen Francis | In Progress | App | No | In Progress | Continue development
HA30-14878 | Dashboard QA Task - Implement the functionality for top 4 KPI cards | Task | Raji S | In Progress | App, QA | No | In Progress | Continue development
HA30-14922 | Medicine Inventory – Available Quantity and Restock Option for “Do Not Track Stock” Medicines | Story |  | In Progress | App, QA | No | Owner needed | Assign owner
HA30-14966 | Medicine Inventory - Other as an option in Treatment type | Story | Praveen Francis | In Progress | App | No | In Progress | Continue development
HA30-15041 | Activity Log - Upload Excel - Add new animal | Story | Praveen Francis | In Progress | App | No | In Progress | Continue development
HA30-15043 | Activity Log - Upload Excel - Update animal info | Story | Praveen Francis | In Progress | App | No | In Progress | Continue development
HA30-15044 | Activity Log - Upload Excel - Add weight history | Story | Praveen Francis | In Progress | App | No | In Progress | Continue development
HA30-15045 | Activity Log - Upload Excel - Add Animal Movement to Animal History | Story | Praveen Francis | In Progress | App | No | In Progress | Continue development
HA30-15047 | Activity Log - Upload Excel - Add Beef programs | Story | Praveen Francis | In Progress | App | No | In Progress | Continue development
HA30-15049 | Activity Log - Search activities in Activity log screen | Story | Praveen Francis | In Progress | App | No | In Progress | Continue development
HA30-15052 | Activity Log - Chute Session - Front end development for activities and details for adding new animals | Story | Praveen Francis | In Progress | App | No | In Progress | Continue development
HA30-15055 | Activity Log - Chute session - Animal Movement | Story | Praveen Francis | In Progress |  | No | In Progress | Continue development
HA30-15056 | Activity Log - Chute session - Weight update | Story | Praveen Francis | In Progress |  | No | In Progress | Continue development
HA30-15076 | Medicine Inventory QA Task – Available Quantity and Restock Option for “Do Not Track Stock” Medicines | Task | gnana sankar | In Progress | App, QA | No | In Progress | Continue development
HA30-15079 | QA Task - Present Animal History Instead of Enclosure Movement History | Task | gnana sankar | In Progress | App, QA | No | In Progress | Continue development
HA30-15193 | Beef Program Details Are Not Displayed Correctly in Activity Log After Upload Excel | Bug | Saravana Kumar M | In Progress | App, Dev, QA | No | In Progress | Continue development
HA30-15209 | Run QA Automation Regression Suite on Staging build 5.0.152 (09) | Task | Mariappan E | In Progress | QAAutomation | No | In Progress | Continue development
HA30-13964 | Connecting to a reader during a session while in manual error | Bug | Samuel Parker | Ready for Testing | App, Dev, QA | No | Ready for Testing | Complete QA validation
HA30-14115 | Feed - Ration Card need to show the Ration Category | Improvement | Abraham | Ready for Testing | App, Dev, QA | No | Ready for Testing | Complete QA validation
HA30-14381 | Backdate feed option auto selecting in add to inventory | Bug | Samuel Parker | Ready for Testing | App, Dev, QA | No | Ready for Testing | Complete QA validation
HA30-14769 | Firebase Crash - HHR - CreateNewAnimalsFormHHRState.startListening.<fn> | Bug | Abraham | Ready for Testing | App, Dev, Firebase, QA | No | Ready for Testing | Complete QA validation
HA30-14785 | Admin portal - Grey screen in Manage Menu screen | Bug | gangappan | Ready for Testing | Admin | No | Ready for Testing | Complete QA validation
HA30-14904 | Switch Lot ID for Deleted Animals - Riley Livestock | Task | Samuel Parker | Ready for Testing |  | No | Ready for Testing | Complete QA validation
HA30-14921 | Avg. Daily Gain Value Is Not Displayed as the Animal’s Highest ADG Value | Bug | Raji S | Ready for Testing | App, Dev, QA | No | Ready for Testing | Complete QA validation
HA30-15215 | Firebase Crash - _LocationReaderContainerState._getSecondaryAntenaFlag.<fn> - Null Error | Bug | Abraham | Ready for Testing | App, Dev, Firebase, QA | No | Ready for Testing | Complete QA validation
HA30-15219 | Firebase Crash - Stage - AnimalEditableInformationState.build. | Bug | Abraham | Ready for Testing | App, Dev, Firebase, QA | No | Ready for Testing | Complete QA validation
HA30-14347 | Display full tag ID for UHF in scan pages (ATI & Select multiple) | Story | Praveen Francis | HerdX Accepted | App | No | HerdX Accepted | Confirm acceptance and close
HA30-14862 | Activity Log - Activities tabular view for Mobile layout | Story | Praveen Francis | HerdX Accepted | App | No | HerdX Accepted | Confirm acceptance and close
HA30-14923 | Dashboard - Add recent activities widget | Story | Praveen Francis | HerdX Accepted | App | No | HerdX Accepted | Confirm acceptance and close
HA30-14930 | Counting Session Not Displaying Tag in Inventory | Bug | Samuel Parker | HerdX Accepted | App, Dev, QA | No | HerdX Accepted | Confirm acceptance and close
HA30-15013 | Visual Tag - Display Full Visual tag in Health, treatments, Breeding & Parentage screens | Story | Praveen Francis | HerdX Accepted | App | No | HerdX Accepted | Confirm acceptance and close
HA30-15028 | Show Text Field When Selecting Other Breed | Task | ajith | HerdX Accepted | App, Dev | No | HerdX Accepted | Confirm acceptance and close
HA30-15051 | Activity Log - Chute session - Add animals | Story | Praveen Francis | HerdX Accepted | App | No | HerdX Accepted | Confirm acceptance and close
HA30-15053 | Activity Log - Chute session - Edit Existing animals | Story | Praveen Francis | HerdX Accepted | App | No | HerdX Accepted | Confirm acceptance and close
HA30-15150 | Not able to type more than one letter in common information (Pen or pasture) | Bug | Abraham | HerdX Accepted | App, Dev, QA | No | HerdX Accepted | Confirm acceptance and close
HA30-15201 | Pregnancy Check – “# of Calves” field cannot be cleared once a value is selected (no “0”/blank option) | Bug | ajith | HerdX Accepted | App, Dev, QA, Tested | No | HerdX Accepted | Confirm acceptance and close
HA30-14976 | Activity Log – Search Bar Automatically Displays Created Item Without User Applying Search (TAB VIEW) | Bug | gangappan | Rejected / Not a Bug | App, Dev, QA | No | Rejected / Not a Bug | Confirm closure
HA30-15192 | Activity Log – Chute Session: Medicine Name Is Not Displayed Properly When Adding Medicine to an Animal | Bug | Raji S | Rejected / Not a Bug | App, QA | No | Rejected / Not a Bug | Confirm closure
HA30-15108 | Activity Log Card Does Not Display Inventory Add or Edit any Activities | Bug | gangappan | Discarded | App, Dev, QA | No | Discarded | Review next action

## Source Data
Key | Summary | Issue Type | Assignee | Status | Labels | Production Bug
HA30-15257 | Production: Activity log- Upload Excel ,Under Treatment details should not be shown | Bug | Allwin. T | Ready for Testing | Dev, Prod, QA | Yes
HA30-15248 | Production - Activity Log Records Are Not Displayed Across All Devices | Bug | Raji S | Done | Dev, Prod, QA | Yes
HA30-15247 | Production Release 1.1.285 (485) for IOS, Android and Web | Task | Abraham | Done | App, Deployment | No
HA30-15226 | Prod Web: Deleted Tag – Deleted Date Ascending/Descending Sort Filter Not Working | Bug | Alpa Mori | Ready for Testing | App, Dev, Prod, QA | Yes
HA30-15225 | Staging Release 5.0.152 (11) for IOS, Android and Web | Task | Abraham | Done | App, Deployment | No
HA30-15223 | Duplicate Activities Are Displayed in Activity Log for a Single Chute Session Movement | Bug | gangappan | New / Open | App, Dev, QA | No
HA30-15220 | Staging Release 5.0.152 (10) for IOS, Android and Web | Task | Abraham | New / Open | App, Deployment | No
HA30-15219 | Firebase Crash - Stage - AnimalEditableInformationState.build. | Bug | Abraham | Ready for Testing | App, Dev, Firebase, QA | No
HA30-15217 | Prod Issue - HSR Reader Name Is Displayed as Null on the all module Scan Page in Offline Mode | Bug | ajith | Done | App, Dev, Prod, QA | Yes
HA30-15216 | Firebase Crash - ConsumerStatefulElement.watch | Bug | Abraham | Done | App, Dev, Firebase, QA | No
HA30-15215 | Firebase Crash - _LocationReaderContainerState._getSecondaryAntenaFlag.<fn> - Null Error | Bug | Abraham | Ready for Testing | App, Dev, Firebase, QA | No
HA30-15214 | Chute session - AI Info not showing, If we disabled the Express Mode | Bug | Abraham | Done | App, Dev, QA | No
HA30-15212 | HerdView SnapView: Animal Status by Sex/Type : "Vaquilla" Is Incorrectly Displayed | Bug | samuel kishore kumar | New / Open | App, Dev, QA | No
HA30-15211 | Herdview SnapView: Data displayed in HerdView SnapView is not matching between the Web and App versions. | Bug | samuel kishore kumar | New / Open | App, Dev, QA | No
HA30-15209 | Run QA Automation Regression Suite on Staging build 5.0.152 (09) | Task | Mariappan E | In Progress | QAAutomation | No
HA30-15207 | Staging Release 5.0.152 (09) for IOS, Android and Web | Task | Abraham | Done | App, Deployment | No
HA30-15206 | Special Characters and Emojis Are Not Restricted in Activity Log Search | Bug | gnana sankar | Done | App, Dev, QA | No
HA30-15204 | Identify and Disable Unnecessary Report Refreshes and Related Jobs | Task |  | New / Open |  | No
HA30-15201 | Pregnancy Check – “# of Calves” field cannot be cleared once a value is selected (no “0”/blank option) | Bug | ajith | HerdX Accepted | App, Dev, QA, Tested | No
HA30-15199 | Run QA Automation Regression Suite on Staging build 5.0.152 (08) | Task | Mariappan E | Done |  | No
HA30-15198 | Cedaco Range Issue - HSR is not assigned to their organization | Bug | Abraham | New / Open | App, Dev, Prod, QA | Yes
HA30-15197 | Activity Log -Treatment Status Is Not Displayed Correctly for Animals with Assigned Treatments | Bug | gnana sankar | Done | App, Dev, QA | No
HA30-15196 | Complete Android developer verification registration | Task | samuel kishore kumar | New / Open | App, Dev | No
HA30-15195 | Activity Log – Upload Excel: Time Is Displayed Incorrectly for Uploaded Fields | Bug | ajith | Done | App, Dev, QA | No
HA30-15194 | Chute Session - Save button not enabled for the new tags | Bug | Abraham | New / Open | App, Dev, QA | No
HA30-15193 | Beef Program Details Are Not Displayed Correctly in Activity Log After Upload Excel | Bug | Saravana Kumar M | In Progress | App, Dev, QA | No
HA30-15192 | Activity Log – Chute Session: Medicine Name Is Not Displayed Properly When Adding Medicine to an Animal | Bug | Raji S | Rejected / Not a Bug | App, QA | No
HA30-15190 | Remove USDA Encode Value from Activity Log | Bug | gnana sankar | Done | App, Dev, QA | No
HA30-15189 | Staging Release 5.0.152 (08) for IOS, Android and Web | Task | Abraham | Done | App, Deployment | No
HA30-15188 | Firebase Crash - Element.widget FlutterError - Null check operator used on a null value | Bug | Abraham | Done | App, Dev, Firebase, QA | No
HA30-15187 | Firebase Crash - (null)._extractReplyValueOrThrow | Bug | Abraham | Done | App, Dev, Firebase, QA | No
HA30-15186 | Run QA Automation Regression Suite on Staging build 5.0.152 (07) | Task | Mariappan E | Done | QAAutomation | No
HA30-15185 | Dev task - Filter Discovery, Index Tuning, Caching | Task | samuel kishore kumar | Done | App, Dev | No
HA30-15184 | Dev task - Enable Firebase Crashlytics Reporting in Staging Environment | Task | samuel kishore kumar | Done | App, Dev | No
HA30-15183 | Dev task - Real-Time Sync Pipeline, Dead-Letter Queue & Health Engine | Task | samuel kishore kumar | Done | App, Dev | No
HA30-15181 | Dev Task - SnapView Report - Database Schema architecture & Data migration engine | Task | samuel kishore kumar | Done | App, Dev | No
HA30-15180 | Activity Log Displays Entire Bulk Operation Instead of the Selected Recent Activity | Bug | gnana sankar | Done | App, Dev, QA | No
HA30-15179 | Activity Log – Show Animal Movement Only for Enclosure-to-Enclosure Updates | Bug | gnana sankar | Done | App, Dev, QA | No
HA30-15178 | Enable Firebase Crashlytics Reporting in Staging Environment | Story | samuel kishore kumar | New / Open | App | No
HA30-15177 | Firebase Crash - MedicineInventoryOfflineAdapter.read - Null Check Issue | Bug | Abraham | Done | App, Dev, Firebase, QA | No
HA30-15176 | Firebase Crash - Provider._inheritedElementOf - Null Check Error | Bug | Abraham | Done | App, Dev, Firebase, QA | No
HA30-15174 | Upload Excel Dev Task - Include Additional IDs in Upload Excel | Task | Alpa Mori | Done | App, Dev | No
HA30-15173 | Firebase Crash - While Navigating from Dashboard in iPhone Crash is coming in Terminal | Bug | Abraham | Done | App, Dev, Firebase, QA | No
HA30-15172 | Tag IDs not Showing Up in Inventory During Chute Session | Bug | Samuel Parker | Ready for Testing | App, Dev, Prod, QA | Yes
HA30-15171 | Feed Information Now Showing Up in Ogle Farms | Bug | Samuel Parker | Ready for Testing | App, Dev, Prod, QA | Yes
HA30-15166 | Dev Task - Geospatial Mapping Engine & Treatment Medicine Analytics | Task | samuel kishore kumar | Done | Dev, app | No
HA30-15165 | Staging Release 5.0.152 (07) for IOS, Android and Web | Task | Abraham | Done |  | No
HA30-15163 | Dev task - SnapView Report - Distribution Analytics: Time on Yard & Demographics | Task | samuel kishore kumar | Done | App, Dev | No
HA30-15161 | Dev Task SnapView Report - Core KPI engine and Financial outcome resolvers | Task | samuel kishore kumar | Done | App, Dev | No
HA30-15160 | Add Medicine Page Opens Multiple Times When Plus Icon Is Clicked Repeatedly | Bug | gnana sankar | Done | App, Dev, QA | No
HA30-15159 | Activity Log - Chute session - Weight update | Task | Allwin. T | Done | ActivityLog, App, ChuteSession, Dev | No
HA30-15158 | Remove “Not Specified” Text from the Web App Navigation Menu | Bug | gnana sankar | Done | App, Dev, QA | No
HA30-15157 | QA Task - Show Text Field When Selecting Other Breed | Task | Abraham | Done | App, QA | No
HA30-15156 | Display Informative Message When Deleting a Breed Assigned to Animals | Improvement | samuel kishore kumar | New / Open | App, Dev, QA | No
HA30-15155 | Activity Log – Chute Process Page: Activity Time Displayed Incorrectly | Bug | Raji S | Done | App, Dev, QA | No
HA30-15154 | Staging Release 5.0.152 (06) for IOS, Android and Web | Task | Abraham | Done |  | No
HA30-15153 | Firebase Crash - UnmodifiableListMixin.remove | Bug | Abraham | Done | App, Dev, Firebase, QA | No
HA30-15152 | Activity Log – Chute Session: Animal Count Not Displayed as 1 After Scanning | Bug | Raji S | Done | App, Dev, QA | No
HA30-15151 | Breed Validation Does Not Prevent Duplicate Breed Entries in “Other” Category | Bug | gnana sankar | Done | App, Dev, QA | No
HA30-15150 | Not able to type more than one letter in common information (Pen or pasture) | Bug | Abraham | HerdX Accepted | App, Dev, QA | No
HA30-15149 | Backdate AI Breeding Date | Task | gangappan | New / Open | App, Dev, QA | No
HA30-15148 | Run QA Automation Regression Suite on Staging build 5.0.152 (05) | Task | Mariappan E | Done | QAAutomation | No
HA30-15147 | Filter Discovery, Index Tuning, Caching | Story | samuel kishore kumar | New / Open | App | No
HA30-15146 | Geospatial Mapping Engine & Treatment Medicine Analytics | Story | samuel kishore kumar | New / Open | App | No
HA30-15145 | Real-Time Sync Pipeline, Dead-Letter Queue & Health Engine | Story | samuel kishore kumar | New / Open | App | No
HA30-15144 | SnapView Report - Distribution Analytics: Time on Yard & Demographics | Story | samuel kishore kumar | New / Open | App | No
HA30-15143 | SnapView Report - Core KPI engine and Financial outcome resolvers | Story | samuel kishore kumar | New / Open | App | No
HA30-15142 | SnapView Report - Database Schema architecture & Data migration engine | Story | samuel kishore kumar | New / Open | App | No
HA30-15141 | Activity Log – Blank Screen Displayed When No Matching Activity Is Found | Bug | ajith | Done | App, Dev, QA | No
HA30-15140 | Activity Log - Chute Session - Front end development for activities and details for adding new animals | Task | Allwin. T | Done | ActivityLog, App, ChuteSession, Dev | No
HA30-15139 | Activity Log – UI Issue on iPad | Bug | Raji S | Done | App, Dev, QA | No
HA30-15138 | Activity Log – “Something went wrong” Message Displayed While Performing Animal Movement in Chute Session | Bug | Raji S | Done | App, Dev, QA | No
HA30-15137 | Dashboard – Activity Log – Notifications Option Is Highlighted Instead of Dashboard After Returning from Activity Log on Tablet | Bug | ajith | Done | App, Dev, QA | No
HA30-15136 | Staging Release 5.0.152 (05) for IOS, Android and Web | Task | Abraham | Done | App, Deployment | No
HA30-15132 | Activity Log - Chute session - Animal Movement | Task | Allwin. T | Done |  | No
HA30-15131 | PROD: Calving Filter Is Not Working | Task | gangappan | New / Open | App, Dev, QA | Yes
HA30-15130 | QA Task - Update other language Sex/type in animal collection to English | Task | Abraham | Done | App, QA | No
HA30-15129 | Dashboard – Activity Log – Incorrect Time Displayed for Upload Excel Add/Edit Activity | Bug | ajith | Done | App, Dev, QA | No
HA30-15128 | Run QA Automation Regression Suite on Staging build 5.0.152 (04) | Task | Mariappan E | Done | QAAutomation | No
HA30-15127 | Update other language Sex/type in animal collection to English | Task | gangappan | Done | App | No
HA30-15126 | Run QA Automation Regression Suite on Production Hot Fix 1.1.284 (484) | Task | Mariappan E | Done | QAAutomation | No
HA30-15125 | Firebase Crash - NewCountingSessionSummaryCubit.refreshToken | Bug | Abraham | Done | App, Dev, Firebase, QA | No
HA30-15124 | Activity Log Page: Filter Is Not Refreshed After Clearing Search Text | Bug | Raji S | Done | App, Dev, QA | No
HA30-15123 | Upload Excel (Add) – Activity Log Is Not Updated Until Manual Sync Is Performed | Bug | ajith | Done | App, Dev, QA | No
HA30-15122 | Activity Log Not Displayed on Dashboard in Offline Mode | Bug | gnana sankar | Done | App, Dev, QA | No
HA30-15121 | Dashboard – Activity Log – Last 14 Days Text and More Button Alignment Issue on Tablet | Bug | ajith | Done | App, Dev, QA | No
HA30-15120 | Firebase Crash - TagsHelper._processTags FlutterError - RangeError (length): Invalid value: Not in inclusive range 0..15: 16 | Bug | Abraham | Done | App, Dev, Firebase, QA | No
HA30-15119 | Staging Release 5.0.152 (04) for IOS, Android and Web | Task | Abraham | Done | App, Deployment | No
HA30-15118 | Production Hot Fix Release 1.1.284 (484) for IOS, Android and Web | Task | Abraham | Done | App, Deployment | No
HA30-15117 | Activity Log - Chute session - Edit Existing animals | Task | Allwin. T | Done | ActivityLog, App, ChuteSession, Dev | No
HA30-15115 | Fix Spanish Value Not Translated to English in Add to Inventory | Task | Gladys Kirubavathi | Done | App | No
HA30-15114 | Implement HerdView SnapView Report in Flutter | Story | Muhundhan E | New / Open | App | No
HA30-15113 | Run QA Automation Regression Suite on Staging build 5.0.152 (03) | Task | Mariappan E | Done | QAAutomation | No
HA30-15112 | Treatment Loader Spins Continuously After Switching Tabs | Bug | gnana sankar | Done | App, Dev, Prod, QA | Yes
HA30-15111 | Run QA Automation Regression Suite on Staging build 5.0.152 (02) | Task | Mariappan E | Done | QAAutomation | No
HA30-15110 | Activity Log – Chute Session Activity Is Displayed When Searching with Non-Matching Text | Bug | ajith | Done | App, Dev, QA | No
HA30-15109 | Dev Task - Implement HerdView SnapView Report in Flutter | Task | Muhundhan E | Done | App, Dev | No
HA30-15108 | Activity Log Card Does Not Display Inventory Add or Edit any Activities | Bug | gangappan | Discarded | App, Dev, QA | No
HA30-15107 | Staging Release 5.0.152 (03) for IOS, Android and Web | Task | Abraham | Done | App, Deployment | No
HA30-15106 | Activity Log - Chute session - Add animals | Task | Allwin. T | Done | ActivityLog, App, ChuteSession, Dev | No
HA30-15103 | Firebase Crash - Element.widget FlutterError - Null check operator used on a null value | Bug | Abraham | Done | App, Dev, Firebase, QA | No
HA30-15102 | Firebase Crash - Provider._inheritedElementOf FlutterError - Provider<ScanTagsCubit> not found for Builder. Error thrown while handling a gesture. | Bug | Abraham | Done | App, Dev, Firebase, QA | No
HA30-15101 | Firebase Crash - View.of FlutterError - Null check operator used on a null value | Bug | Alpa Mori | New / Open | App, Dev, Firebase, QA | No
HA30-15100 | PROD: Cedaco Ranch - Counting Session Export Issue | Bug | Candace Adams | HerdX Accepted | App, Dev, Prod, QA | Yes
HA30-15098 | Medicine Inventory Dev Task - Other as an option in Treatment type | Task | Alpa Mori | Done | App, Dev | No
HA30-15097 | Staging Release 5.0.152 (02) for IOS, Android and Web | Task | Abraham | Done | App, Deployment | No
HA30-15096 | Activity Log - Search activities in Activity log screen | Task | Allwin. T | Done |  | No
HA30-15095 | Firebase Crash - ProviderScope.containerOf | Bug | Abraham | Done | App, Dev, Firebase, QA | No
HA30-15094 | Activity Log QA Task - Chute session - Animal Movement | Task | Raji S | Done | App, QA | No
HA30-15093 | Activity Log - Chute Session QA Task - Front end development for activities and details for adding new animals | Task | Raji S | Done | App, QA | No
HA30-15091 | Activity Log QA Task - Chute session - Add animals | Task | Raji S | Done | App, QA | No
HA30-15090 | Activity Log QA Task- Chute session - Edit Existing animals | Task | Raji S | Done | App, QA | No
HA30-15089 | Activity Log QA Task - Chute session - Weight update | Task | Raji S | Done | App, QA | No
HA30-15088 | Activity Log QA Task- Upload Excel - Add weight history | Task | ajith | Done | App, QA | No
HA30-15087 | Activity Log QA Task- Upload Excel - Add new animal | Task | ajith | Done | App, QA | No
HA30-15086 | Activity Log QA Task- Upload Excel - Update animal info | Task | ajith | Done | App, QA | No
HA30-15085 | Activity Log QA Task- Add Animal Movement to Animal History | Task | gnana sankar | Done | App, QA | No
HA30-15084 | Activity Log QA Task - Upload Excel - Add Beef programs | Task | ajith | Done | App, QA | No
HA30-15083 | Activity Log QA Task - Search activities in Activity log screen | Task | ajith | Done | App, QA | No
HA30-15082 | QA Task - Display full tag ID for UHF in scan pages (ATI & Select multiple) | Task | Abraham | Done | App, QA | No
HA30-15081 | Activity log QA Task - Implement total activities KPI functionality | Task | gnana sankar | Done | App, QA | No
HA30-15080 | Counting Session QA Task- Performance analysis for storing session data in Reader sessions | Task | Abraham | Done | App, QA | No
HA30-15079 | QA Task - Present Animal History Instead of Enclosure Movement History | Task | gnana sankar | In Progress | App, QA | No
HA30-15078 | Medicine Inventory QA Task - Other as an option in Treatment type | Task | Abraham | Done | App, QA | No
HA30-15077 | Visual Tag QA Task - Display Full Visual tag in Health, treatments, Breeding & Parentage screens | Task | Abraham | Done | App, QA | No
HA30-15076 | Medicine Inventory QA Task – Available Quantity and Restock Option for “Do Not Track Stock” Medicines | Task | gnana sankar | In Progress | App, QA | No
HA30-15075 | QA Task - Counting session - Add Counting session ID in Reader sessions | Task | Abraham | Done | App, QA | No
HA30-15074 | Staging Release 5.0.152 (01) for IOS, Android and Web | Task | Abraham | Done | App, Deployment | No
HA30-15073 | Deployment for Sprint 101 | Story | Abraham | New / Open | App, Deployment | No
HA30-15072 | Prod Issue - ATI R6 – Tag Counts Are Not Displayed in Preexisting Tags and Not Assigned to This Org Sections After Returning to Session Summary | Bug | ajith | Done | App, Dev, Prod, QA | Yes
HA30-15071 | Prod - ATI - Spanish - Added Animal sex type save in Spanish in Firebase DB | Bug | Abraham | Done | App, Dev, Prod, QA, Regression | Yes
HA30-15070 | Prod - Not able to create location to location Transfer | Bug | Abraham | Cannot Reproduce | App, Dev, Prod, QA, Regression | Yes
HA30-15069 | Prod Issue - Select All and Unselect Actions Not Working in Select Multiple Flow | Bug | gnana sankar | Done | App, Dev, Prod, QA | Yes
HA30-15067 | Activity Log Dev Task - Upload Excel - Add Beef programs | Task | Alpa Mori | Done | App, Dev | No
HA30-15065 | Activity Log Dev Task - Add Animal Movement to Animal History | Task | Alpa Mori | Done | App, Dev | No
HA30-15063 | Activity Log Dev Task - Upload Excel - Add weight history | Task | Alpa Mori | Done | App, Dev | No
HA30-15061 | Activity Log Dev Task - Upload Excel - Update animal info | Task | Alpa Mori | Done | App, Dev | No
HA30-15059 | Activity Log Dev Task - Upload Excel - Add new animal | Task | Alpa Mori | Done | App, Dev | No
HA30-15057 | Activity Log Dev Task - Common function for Upload Excel | Task | Alpa Mori | Done | App, Dev | No
HA30-15056 | Activity Log - Chute session - Weight update | Story | Praveen Francis | In Progress |  | No
HA30-15055 | Activity Log - Chute session - Animal Movement | Story | Praveen Francis | In Progress |  | No
HA30-15054 | Run QA Automation Regression Suite on Production build 1.1.283 (483) | Task | Mariappan E | Done | QAAutomation | No
HA30-15053 | Activity Log - Chute session - Edit Existing animals | Story | Praveen Francis | HerdX Accepted | App | No
HA30-15052 | Activity Log - Chute Session - Front end development for activities and details for adding new animals | Story | Praveen Francis | In Progress | App | No
HA30-15051 | Activity Log - Chute session - Add animals | Story | Praveen Francis | HerdX Accepted | App | No
HA30-15050 | Activity log - Implement total activities KPI functionality | Task | Allwin. T | Done | ActivityLog, App, ChuteSession, Dev | No
HA30-15049 | Activity Log - Search activities in Activity log screen | Story | Praveen Francis | In Progress | App | No
HA30-15047 | Activity Log - Upload Excel - Add Beef programs | Story | Praveen Francis | In Progress | App | No
HA30-15045 | Activity Log - Upload Excel - Add Animal Movement to Animal History | Story | Praveen Francis | In Progress | App | No
HA30-15044 | Activity Log - Upload Excel - Add weight history | Story | Praveen Francis | In Progress | App | No
HA30-15043 | Activity Log - Upload Excel - Update animal info | Story | Praveen Francis | In Progress | App | No
HA30-15042 | UI Issue on Add Dose Details Page | Bug | Raji S | Done | App, Dev, QA | No
HA30-15041 | Activity Log - Upload Excel - Add new animal | Story | Praveen Francis | In Progress | App | No
HA30-15040 | Activity Log - Common function for Upload Excel | Story | Alpa Mori | New / Open |  | No
HA30-15036 | Counting Session Dev Task - Add Counting session ID in Reader sessions | Task | Muhundhan E | Done | App, Dev | No
HA30-15035 | Counting Session Dev Task - Performance analysis for storing session data in Reader sessions | Task | Muhundhan E | Done | App, Dev | No
HA30-15033 | Dev Task - Display full tag ID for UHF in scan pages (ATI & Select multiple) | Task | Muhundhan E | Done | App, Dev | No
HA30-15032 | Chute Session: Restock Medicine Bug | Bug | Raji S | Done | App, Dev, QA | No
HA30-15029 | Bugs with Adding Sources | Bug | Samuel Parker | Ready for Testing | App, Dev, Prod, QA | Yes
HA30-15028 | Show Text Field When Selecting Other Breed | Task | ajith | HerdX Accepted | App, Dev | No
HA30-15027 | Chute - Specific Info Medicine not listing | Bug | Abraham | Done | App, Dev, QA | No
HA30-15023 | Firebase Crash - Stargate._stopScan | Bug | Abraham | Done | App, Dev, Firebase, QA | No
HA30-15022 | Firebase Crash - VectorGraphicWidgetState._loadPicture.<fn> | Bug | Abraham | Done | App, Dev, Firebase, QA | No
HA30-15021 | Firebase Crash - QRViewController.pauseCamera | Bug | Abraham | Done | App, Dev, Firebase, QA | No
HA30-15013 | Visual Tag - Display Full Visual tag in Health, treatments, Breeding & Parentage screens | Story | Praveen Francis | HerdX Accepted | App | No
HA30-15008 | Azure Cost Analysis – Databricks Long-Running Job | Bug | Gladys Kirubavathi | In Progress | Analytics, Prod | Yes
HA30-15001 | Validate R6 Reader Output Power Based on Detection Setting | Task | Allwin. T | Done | App, Dev, r6Scan | No
HA30-14997 | Validate R6 Reader Output Power Based on Detection Setting | Story | Allwin. T | New / Open |  | No
HA30-14979 | Activity Log – “Treatment Added” Records Are Not Displayed and Undo Button is missing (Tab View) | Bug |  | New / Open | App, Dev, QA | No
HA30-14977 | Activity Log – Undo Button Is Missing for “Add to Inventory” Activity(TAB VIEW) | Bug | Raji S | New / Open | App, Dev, QA | No
HA30-14976 | Activity Log – Search Bar Automatically Displays Created Item Without User Applying Search (TAB VIEW) | Bug | gangappan | Rejected / Not a Bug | App, Dev, QA | No
HA30-14966 | Medicine Inventory - Other as an option in Treatment type | Story | Praveen Francis | In Progress | App | No
HA30-14934 | Dashboard QA Task - Add recent activities widget | Task | ajith | Done | App, QA | No
HA30-14930 | Counting Session Not Displaying Tag in Inventory | Bug | Samuel Parker | HerdX Accepted | App, Dev, QA | No
HA30-14923 | Dashboard - Add recent activities widget | Story | Praveen Francis | HerdX Accepted | App | No
HA30-14922 | Medicine Inventory – Available Quantity and Restock Option for “Do Not Track Stock” Medicines | Story |  | In Progress | App, QA | No
HA30-14921 | Avg. Daily Gain Value Is Not Displayed as the Animal’s Highest ADG Value | Bug | Raji S | Ready for Testing | App, Dev, QA | No
HA30-14911 | Report QA Task - Treatment report functionality - Mobile & Tab version | Task | gnana sankar | Done | App, QA | No
HA30-14904 | Switch Lot ID for Deleted Animals - Riley Livestock | Task | Samuel Parker | Ready for Testing |  | No
HA30-14898 | Present Animal History Instead of Enclosure Movement History | Story |  | New / Open | App | No
HA30-14883 | Production – Multiple Diagnosis Options Missing in Health & Treatment Module | Bug | Mariappan E | Done | App, QAAutomation, Tested | No
HA30-14882 | Activity Log QA Task - Display activity type breakdown in pie chart | Task | Abraham | Done | App, QA | No
HA30-14881 | Activity Log QA Task- Activities Tabular view UI for Tab and Web | Task | Raji S | Done | App, QA | No
HA30-14880 | Activity Log QA Task- Activities tabular view for Mobile layout | Task | gnana sankar | Done | App, QA | No
HA30-14878 | Dashboard QA Task - Implement the functionality for top 4 KPI cards | Task | Raji S | In Progress | App, QA | No
HA30-14877 | Dashboard QA Task - Breeds pie chart | Task | gnana sankar | Done | App, QA | No
HA30-14873 | Dashboard QA Task - UI for Top 4 KPI cards on Dashboard | Task | gnana sankar | Done | App, QA | No
HA30-14871 | Visual Tag Dev Task - Display Full Visual tag in Health, treatments, Breeding & Parentage screens | Task | Muhundhan E | Done | App, Dev | No
HA30-14870 | Activity log - Implement total activities KPI functionality | Story | Praveen Francis | In Progress | App | No
HA30-14862 | Activity Log - Activities tabular view for Mobile layout | Story | Praveen Francis | HerdX Accepted | App | No
HA30-14861 | Activity Log - Activities Tabular view UI for Tab and Web | Story | Praveen Francis | In Progress | App | No
HA30-14857 | Activity Log - Display activity type breakdown in pie chart | Story | Praveen Francis | In Progress | App | No
HA30-14834 | Dashboard STR - Breeds pie chart | Story | Praveen Francis | In Progress | App | No
HA30-14833 | Dashboard STR - Implement the functionality for top 4 KPI cards | Story | Alpa Mori | New / Open | App | No
HA30-14832 | Dashboard STR - UI for Top 4 KPI cards on Dashboard | Story | Praveen Francis | In Progress | App | No
HA30-14826 | Investigate Azure ADF Cost Increase and Identify Cost Optimization Opportunities | Task | Gladys Kirubavathi | In Progress | Analytics, App | No
HA30-14822 | Report Story - Treatment report functionality - Mobile & Tab version | Story | Praveen Francis | In Progress | App, POC | No
HA30-14816 | Review and Resolve All Crashlytics Issues in the Chute session | Story | Praveen Francis | In Progress | App | No
HA30-14814 | Prevent Data Loss by Stopping Process on Critical Errors in inventory | Story | Praveen Francis | In Progress | App | No
HA30-14813 | New Automation Development – Assign Medicine to Animals for Pastures from Medicine Inventory | Story | Mariappan E | In Progress | QAAutomation | No
HA30-14798 | Prod Issue - Customer Issue - Animals Missing in the Chute session | Bug | Praveen Francis | New / Open | App, Dev, Prod, QA | Yes
HA30-14785 | Admin portal - Grey screen in Manage Menu screen | Bug | gangappan | Ready for Testing | Admin | No
HA30-14779 | Prod : Treatment history continuous sync | Bug | Samuel Parker | Ready for Testing | App, Dev, Prod, QA | Yes
HA30-14769 | Firebase Crash - HHR - CreateNewAnimalsFormHHRState.startListening.<fn> | Bug | Abraham | Ready for Testing | App, Dev, Firebase, QA | No
HA30-14734 | Firebase Extensions decommission on Mar 31, 2027 | Task | samuel kishore kumar | New / Open |  | No
HA30-14635 | Counting session - Add Counting session ID in Reader sessions | Story | Praveen Francis | In Progress | App | No
HA30-14634 | Counting Session - Performance analysis for storing session data in Reader sessions | Story | Praveen Francis | In Progress | App | No
HA30-14596 | Investigate inconsistent HSR RFID tag reading performance during load-out at Riley Livestock | Task | Abraham | New / Open |  | No
HA30-14595 | Access to the Google Cloud console | Task | samuel kishore kumar | New / Open |  | No
HA30-14594 | Azure Databricks workspace entitlement changes | Task | Gladys Kirubavathi | New / Open |  | No
HA30-14471 | Prod - MedicineInventory - Other medicine type not listed in user medicine, Old version if we update other medicine type , its shown blank in new app | Bug | Samuel Parker | Ready for Testing | App, Dev, Prod, QA | Yes
HA30-14460 | Shift Spacing on Inventory Page for Desktop Version | Improvement | Saravana Kumar M | New / Open |  | No
HA30-14422 | Prod -Web ,For Location Operation User other location records were displayed | Bug | gangappan | New / Open | App, Prod, QA, dev, web | Yes
HA30-14419 | Firebase Crash - Provider._inheritedElementOf FlutterError - Provider<ScanTagsCubit> not found for Builder. Error thrown while handling a gesture. | Bug | Abraham | Done | App, Dev, Firebase, QA | No
HA30-14381 | Backdate feed option auto selecting in add to inventory | Bug | Samuel Parker | Ready for Testing | App, Dev, QA | No
HA30-14347 | Display full tag ID for UHF in scan pages (ATI & Select multiple) | Story | Praveen Francis | HerdX Accepted | App | No
HA30-14319 | Export Excel – Improve Alignment of the Glass Tag/Implant Column Within the Additional IDs Group | Improvement | samuel kishore kumar | New / Open |  | No
HA30-14249 | ATI - Manual entry - Message needs to be updated when switching from one tag type to another | Improvement |  | New / Open | App | No
HA30-14115 | Feed - Ration Card need to show the Ration Category | Improvement | Abraham | Ready for Testing | App, Dev, QA | No
HA30-13964 | Connecting to a reader during a session while in manual error | Bug | Samuel Parker | Ready for Testing | App, Dev, QA | No
HA30-13493 | Norton Client Issue in Production - Assigned Tag Range Displayed as "Not Assigned" in Add to Inventory Flow | Bug | Praveen Francis | New / Open | App, Dev, Prod, QA | Yes
HA30-13467 | Crash analytics - R6ReaderCardAndroidState.r6Item. | Bug | Abraham | New / Open | App, Dev, Firebase, QA | No